## PIS
PROJECT INFORMATION SHEET
BASIC FACTS
| Approval of the Project by the World Bank Board | 29 August 2013
| Official beginning of the Project | 04 November 2013
| Date of the Mid-term Review | 21 March 2016
| Closing date | 31 January 2018
| Total GEF Budget (US$) | 3000000
| Total parallel financing (US$) | 15890000
KEY OUTCOMES
|  | END 2015 | TARGET 2016 | END TARGET
| Disbursement rate of GEF Funds | 18% | 50% | 80-100%
| Number of Steering Committee meetings | 2 | 4 | 6
| Area under biodiversity protection (ha) | 0 | 20000 | 30000
| Number of beneficiaries (alternative livelihoods) | 0 | 1000 | 1600
| Percentage of female beneficiaries (%) | 0 | 15 | 30
| Number of community-based sub-projects for alternative livelihoods | 1 | 2 | 4
| Number of MPAs prepared / updated | 0 | 3 | 4
| Number of capacity building initiatives organized by the Project | 18 | 35 | 60
| Total number of beneficiairies of capacity building initiatives | 159 | 250 | 350
| Total number of female beneficiaires of capac. building initiatives | 14 | 30 | 60
| Percentage of female beneficiairies of capac. building initiatives | 8.805 | 12 | 17.1429
| Total number of knowledge products completed & communicated | 16 | 30 | 45
| Total number of documents posted on the Web site | 0 | 30 | 60
| Number of visitors of Project Web site (cumulatif) | 0 | 200 | 800

## Fram
Global PDO INDICATORS
Indicator | Core | Unit measure | Baseline | TARGET VALUE |  |  | Actual implem rate (%)
|  |  |  | End 2015 | Cumulative | End Target |  | GENERAL REMARKS
INDICATOR 1: Marine areas brought under biodiversity protection (ha) (Core) | * | Ha | 0 | 0 | 0 | 40000 | 0 | Bi-annual verification
INDICATOR 2: Direct project beneficiaries (Number) | * | Number | 0 | 20 | 20 | 3000 | 0.66667 | Bi-annual verification.
INDICATOR 3: Number of alternative livelihood projects realized by communities |  | Number | 0 | 1 | 1 | 4 | 25 | Bi-annual verification
INDICATOR 4: Availability of harmonized parameters and database for PERSGA member countries(Yes=1: No= 0)) |  | Yes/No | No | 1 | 1 | 1 | 100 | Bi-annual verification
INDICATOR 5: Female beneficiaries (%) | * | % | 0 | 0 | 0 | 30 | 0 | Bi-annual verification
Intermediate Indicators
INDICATOR | Core | Unit measure | Baseline | TARGET VALUE |  |  | Actual implem rate (%)
|  |  |  | End 2015 | Cumulative | End Target |  | GENERAL REMARKS
INDICATOR 1: Participants in consultation activities during project implementation (number) | * | Number | 0 | 159 | 159 | 400 | 39.75 | Based on monitoring reports
INDICATOR 2: Participants in consultation activities during project implementation - female (Number) | * | Number | 0 | 14 | 14 | 120 | 11.6667 | Based on monitoring reports
Indicator 1.1: Number of MPA plans updated with community input and with assigned rights for user groups |  | Number | 0 | 0 | 0 | 2 | 0 | Based on annual monitoring reports
Indicator 1.2: Number of stakeholders trained and participating in developing/ updating MPA master plans with a rights based approach |  | Number | No | 74 | 74 | 100 | 74 | Based on annual monitoring reports
Indicator 1.3: Rights based management system established in two pilot MPA sites for community user groups (Yes=1; No=0) |  | Y/N | 0 | 1 | 1 | 1 | 100 | Based on annual monitoring reports
Indicator 1.4: Number of institutional MPA staff trained to work with local communities and in rights based approach |  | Number | 0 | 0 | 0 | 10 | 0 | Based on annual monitoring reports
Indicator 1.5: Number of participants from five PERSGA member countries in regional meetings/ exchanges for MPA counterparts on community-based MMA management |  | Number | 0 | 43 | 43 | 45 | 95.5556 | Based on meeting record with lists of participants.
Indicator 1.6: Availability of documentation of lessons learned from regional meetings/ exchanges for MPA counterparts (Yes=1; /No=0) |  | Y/N | 0 | 1 | 1 | 1 | 100 | Based on brochures and records of dissemination events (quarterly).
Indicator 1.7: Percentage of community members involved in MPA plan updating and management who are women |  | % | 0 | 8.805 | 14 | 20 | 44.0252 | Base on project annual reports
Indicator 2.1 Percentage of fishermen involved in fisheries monitoring/ control / surveillance | * | % | 0 | 70 | 0 | 70 | 100 | Based on annual reports on fisheries statistics and monitoring reports
Indicator 2.2: Spawning sites for groupers, snapper and other species under protection (Yes=1; No=0) | * | Y/N | 0 | 0 | 0 | 1 | 0 | Based on annual project monitoring reports
Indicator 2.3: Percentage of variance in groupers |  | % | 0 | 8 | 8 | 15 | 53.3333 | Based on bi-annual baseline reports on fisheries statistics and monitoring reports.
Indicator 2.4 : Percentage of variance in corals |  | % | 0 | 0 | 0 | 15 | 0 | Based on bi-annual baseline reports on fisheries statistics and monitoring reports
Indicator 2.5: Percentage of female beneficiaries of alternative livelihoods subprojects |  | % | 0 | 0 | 0 | 30 | 0 | Based on project annual reports.
Indicator 3.1: Number of PERSGA member country staff trained in common monitoring parameters and methods |  | Number | 0 | 43 | 43 | 40 | 107.5 | Based on project annual reports.
Indicator 3.2: Number of member country routinely employing the monitoring methods developed by PERSGA | * | Ha | 0 | 2 | 2 | 5 | 40 | Based on project annual reports.
Indicator 3.3: Number of regional exchanges on data collection and findings from new parameter | * | Number | 0 | 1 | 1 | 3 | 33.3333 | Based on project annual reports.
Indicator 3.4: Reporting on GEF IW indicators and participation in workshops (Yes=1; /No=0) |  | Number | 0 | 1 | 1 | 1 | 100 | Based on GEF Tracking tools
ADDITIONAL INTERMEDIATE INDICATORS
Number of reviews of fishery laws and policies completed | 2
Number of reviews of monitoring-related documents | 4
Number of documents on socioeconomic, ecological, biological, chemical and other data collected | 2
Number of climate change-related assessments / reports produced | 0
Number of sub-projects identified, developed and implemented by local communities | 0
Total number of papers, reports, documents produced | 16
Number of briefs, policy and practice papers produced and posted on Web | 0
Creation of Web site (Yes=1; No= 0) | 0
Number of documents posted on Web | 0
Number of visitors of Project Web site | 0

## Cap
CAPACITY BUILDING (including all the activities from different components) | [5 empty] | (Only green cell to be manually filled) |  |  |  |  | Numbers in RED to be updated
ACTIVITIES
ACTIVITY |  | Total budget disbursed (end 2015) | PLANNING 2016 |  |  |  | TOTAL CUMULATIVE PLANNED (2015-2016) | PLANNING 2017 |  |  |  |  | TOTAL PLANNED 2017 | COMPLETED in 2016 |  |  |  | COMPLETED in 2017 |  |  |  |  | TOTAL ACTIVITIES COMPLETED | % of completion |  | Number beneficiaries
| Situation at the end of 2015 |  | Jan-Mar 16 | Apr-Jun 16 | Jul-Sep 16 | Oct- Dec 16 |  | Jan-Mar 17 | Apr-Jun 17 | Jul-Sep 17 | Oct- Dec 17 | 2018-01-01 |  | Jan-Mar 16 | Apr-Jun 16 | Jul-Sep 16 | Oct- Dec 16 | Jan-Mar 17 | Apr-Jun 17 | Jul-Sep 17 | Oct- Dec 17 | 2018-01-01 |  |  | Type Beneficiary (Y=1; N=0) |  |  | Inst staff | Nat staff | TOTAL | Female beneficiaries |  |  | % of female benefic.
A. Number of workshops on strengthening Marine management concept in MPAs (Component 1) | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | #DIV/0! | PCU & Nat coordinat. |  |  | 0 | 0 | 0 |  |  | 0 |  | TOTAL | 8.805 | 8.805
B. Number of workshops on legislation, strategies and policies (Component 2) | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | #DIV/0! | Community |  |  | 0 |  |  |  |  | 0
C. Number of workshops on strengthening coastal communities (Component 2) | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #DIV/0! | Community |  |  | 0 |  |  |  |  | 0
D. Workshops on Environmental and Socioeconomic Monitoring (Component 3) | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | #DIV/0! | Miscellanea |  |  | 0 |  |  |  |  | 0
E. Exchange workshops, tour visits, international events, etc. (Component 4) | 2 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | #DIV/0! | Monitoring staff |  |  | 0 |  |  |  |  | 0
|  | 0 |  |  | TOTAL |  | 0 |  |  |  | TOTAL |  | 0 | [7 empty] | TOTAL |  | 18 | #DIV/0!
Workshops / Events: Cumulative number (2015-2016-2017) | 18 | [23 empty] | Sub-TOTAL beneficiaries at the end of 2015 |  | 159 |  |  | Sub-TOTAL female beneficiaries at the end of 2015 |  | 14
[25 empty] | TOTAL updated number of beneficiaries |  |  | 159 |  | TOTAL updated number of female beneficiaries |  |  | 14
SYNTHETIC VIEW
| END 2015 | NEW VALUE
Participants in consultation activities during project implementation (number) | 159 | 159
Participants in consultation activities during project implementation - female (Number) | 14 | 14
Number of stakeholders trained and participating in developing/ updating MPA master plans with a rights based approach | 74 | 74
Rights based management system established in two pilot MPA sites for community user groups (Yes=1; No=0) | 1 | 1
Number of institutional MPA staff trained to work with local communities and in rights based approach | 0 | 0
Number of participants from five PERSGA member countries in regional meetings/ exchanges for MPA counterparts on community-based MMA management | 43 | 43
Availability of documentation of lessons learned from regional meetings/ exchanges for MPA counterparts (Yes=1; /No=0) | 1 | 1
Percentage of community members involved in MPA plan updating and management who are women | 8.805 | 8.805
Number of member country routinely employing the monitoring methods developed by PERSGA | 2 | 2
Number of regional exchanges on data collection and findings from new parameters | 0 | 0
Reporting on GEF IW indicators and participation in workshops (Yes=1; No=0) | 1 | 1
FINANCIAL DATA | 2015 | 2015-2016
Total 2014-2015 Disbursments for capacity building | 0 | 0

## MPA
PREAPARATION AND IMPLEMENTATION OF MANAGEMENT PLANS IN MPAs |  |  |  | (Only green cell to be manually filled) | [17 empty] | TOTAL COMPLETED
ACTIVITY | Already completed in 2014-2015 | PLANNED |  |  |  | PLANNED |  |  |  |  | TOTAL PLANNED | Total Budget allocated | COMPLETED | [8 empty] | TOTAL COMPLETED | % of completion | Number of MPA being implemented | Area brought under protection end 2015 | Area brought under protection
|  | Jan-Mar 16 | Apr-Jun 16 | Jul-Sep 16 | Oct- Dec 16 | Jan-Mar 17 | Apr-Jun 17 | Jul-Sep 17 | Oct- Dec 17 | 2018-01-01 |  |  | Jan-Mar 16 | Apr-Jun 16 | Jul-Sep 16 | Oct- Dec 16 | Jan-Mar 17 | Apr-Jun 17 | Jul-Sep 17 | Oct- Dec 17 | 2018-01-01
A. SUDAN MPA: Dungonab Bay and Mukkawar Island National Park
1. PLANNING
1. 1 Plan prepared and/or updated (with community participation) | 0 | [9 empty] | 0 | 0 | [9 empty] | 0 | #DIV/0! | 0
1.2 Percentage of women among people preparing plan | 0
1.3 Right based system established (Y=1; /N= 0) | 0
1.4 Area brought under biodiversity protection | 0 | [20 empty] | 0 | #DIV/0! |  | 0 | 0
2. ALTERNATIVE LIVELIHOODS
2.1 Fish processing activities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2.2 Recreational fishing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2.3 Eco-tourism | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2.4 Small-scale aquaculture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2.5 Job creation | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | #DIV/0!
2.6 Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL number of community-based sub-project for alternative livelihoods | 1 | [8 empty] | TOTAL | 0 | 0 | [9 empty] | 1 | #DIV/0!
NUMBER of BENEFICIARIES OF ALTERNATIVE LIVELIHOODS
Situation End of 2015 | 20
Total number of beneficiaries during 2016-2017 | 0
Cumulative number of beneficiaries (2015-2017) | 20
Number of female beneficiaries end 2015 | 0
Percentage of female beneficiairies end 2015 | 0
Cumul. number of female beneficiaries (2015-2017) | 0
Percentage of women beneficiaries (2015-2017) | 0
3. MONITORING
3 1 Fishermen involved in community-based monitoring activities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
3.2 Spawning sites under protection with community compliance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
3.3 Percentage variance in groupers (%) | 2.5 | [9 empty] | 15% | [10 empty] | 2.5 | 1666.6667
3.4 Percentage variance in corals | 0% | [9 empty] | 15% | [10 empty] | 0% | 0
B. EGYPT MPA: Wadi El Jimal, Hamata
1. 1 Plan prepared and/or updated (with community participation) | 0 | [9 empty] | 0 | 0 | [9 empty] | 0 | #DIV/0! | 0
2.1 Provision of equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
2.2 Fishermen involved in monitoring activities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2.3 Supporting tourstic accomodations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2.4 Provision of training to rangers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2.5 Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2.6 Area brought under biodiversity protection | 0 | [20 empty] | 0 | #DIV/0! |  |  | 0
C. JORDAN: Aqaba Marine Park
3.1 Provision of equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
3.2 Fishermen involved in monitoring activities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
3.3 Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
3.4 Area brought under biodiversity protection | 0 | [20 empty] | 0 | #DIV/0! |  |  | 0
D. DJIBOUTI : Musha and Maskali Islands MPA
4.1 Fishermen involved in monitoring activities | 0 | [20 empty] | 0
4.2 Socio-economic assessments | 0 | [20 empty] | 0
4.3 Area brought under biodiversity protection | 0 | [20 empty] | 0 | #DIV/0! |  |  | 0
SYNTHESIS
| End 2015 | 2016-2017
Number of management plans prepared/updated | 0 | 0
Area brought under biodiversity protection (ha) | 0 | 0
Number of total beneficiaries of alternative livelihoods | 20 | 20
Percentage of female beneficairies of alternative livelihoods | 0 | 0
Number of sub-projects for alternative livelihoods | 1 | 1
Fishermen involved in monitoring activities | 0 | 0

## Know
KNOWLEDGE PRODUCTS: STUDIES, ASSESSMENTS, REPORTS, MANUALS | [7 empty] | (Only green cell to be manually filled)
ACTIVITY | ALREADY COMPLETED | PLANNED ACTIVITIES (2016-2017) | [8 empty] | TOTAL PLANNED (2016-2017) | ACTIVITIES COMPLETED (2016-2017) | [8 empty] | TOTAL CUMULATIVE ACTIVITIES COMPLETED | TOTAL EXPENDITURES (2015-2017)
|  | Jan-Mar 16 | Apr-Jun 16 | Jul-Sep 16 | Oct- Dec 16 | Jan-Mar 17 | Apr-Jun 17 | Jul-Sep 17 | Oct- Dec 17 | 2018-01-01 |  | Jan-Mar 16 | Apr-Jun 16 | Jul-Sep 16 | Oct- Dec 16 | Jan-Mar 17 | Apr-Jun 17 | Jul-Sep 17 | Oct- Dec 17 | 2018-01-01
1. Comparative review of fisheries laws and policies | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
2. Development of right-based systems in pilot site | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
3. Reviews of current Monitoring & Evaluation parameters | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4. Collection of socioeconomic, ecological, biological, chemical data | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
5. Climate-change related assessments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. Briefs, Practice Paper and Policy Papers produced and disseminated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | TOTAL | 0 | [8 empty] | TOTAL | 16 | 0
TOTAL number of documents produced (at the end of 2015) | 16
TOTAL number of documents produced during 2016-2017 | 0
TOTAL cumulative number of documents produced (2015-2017) | 16
Availability of documentation on lessons learned (Yes=1; No=0) | 1
Total number of documents posted on the Web site | 0
Cumulative number of visitors of Project Web site | 0
MONITORING DATA | End 2015 | 2016-2017
Indicator 2.2: Spawning sites for groupers, snapper and other species under protection (Yes=1; No=0) | 0 | 0
Indicator 2.3: Percentage of variance in groupers | 8 | 8
Indicator 2.4 : Percentage of variance in corals | 0 | 0
FINANCIAL DATA
Total 2014-2015 Disbursements for communication and knowledge sharing | 0
Total 2017 disbursements for Communication and knowledge sharing | 0

## Expend
FINANCIAL PERFORMANCE & EXPENDITURES |  |  |  | (source: Project IFRs)
Component 1: Strengthenining Marine management concept in MPAs
Budget lines | Category | Y 1 | Y 2 | Y 3 | Y 4 | TOTAL | Cumulative Expenditure Dec 2015 | % Actual Expenditures Dec 2015 | Total Expected Dec 2015 | % Expected Dec 2015 | Cumulative Expenditure Dec 2016 | % Actual Expenditures Dec 2016 | Total Expected Dec 2016 | % Expected Dec 2016 | Cumulative Expenditure Dec 2016 | % Actual Expenditures Dec 2016 | Total Expected Dec 2016 | % Expected Dec 2016
21.01/ 21.02 | Consultancy | 95000 | 35000 | 0 | 0 | 130000
21.03/21.04/21.07/21.08 | Training | 70000 | 105000 | 105000 | 20000 | 300000
21.05 | Consult./Workshops |  | 10000 | 10000 | 10000 | 30000
21.06 | Goods/works | 0 | 75000 | 115000 | 50000 | 240000
21.09 | Contingency | 10000 | 15000 | 15000 | 10000 | 50000
TOTAL |  | 175000 | 240000 | 245000 | 90000 | 750000 | 146441 | 19.5255 | 415000 | 55.3333 | 0 | 0 | 660000 | 88 | 0 | 0 | 750000 | 100
Component 2: Strengthenining Coastal Communities
Budget lines | Category | Y 1 | Y 2 | Y 3 | Y 4 | TOTAL | Cumul Expend Dec 2015 | % Expenditure | Total Expected Dec 2015 | % Expected Dec 2015 | Cumulative Expenditure Dec 2016 | % Actual Expenditures Dec 2016 | Total Expected Dec 2016 | % Expected Dec 2016 | Cumulative Expenditure Dec 2016 | % Actual Expenditures Dec 2016 | Total Expected Dec 2016 | % Expected Dec 2016
22.01,02,.04,06,07 | Consultancy | 100000 | 30000 | 20000 | 0 | 150000
21.03/21.04/21.07/ | Training | 70000 | 95000 | 90000 | 15000 | 270000
22.09 | Goods/works | 0 | 100000 | 140000 | 140000 | 380000
TOTAL |  | 170000 | 225000 | 250000 | 155000 | 800000 | 157636 | 19.7045 | 395000 | 49.375 | 0 | 0 | 645000 | 80.625 | 0 | 0 | 0 | 0
Component 3: Environmental Socioeconomic monitoring
Budget lines | Category | Y 1 | Y 2 | Y 3 | Y 4 | TOTAL | Cumul Expend Dec 2015 | % Expenditure | Total Expected Dec 2015 | % Expected Dec 2015 | Cumulative Expenditure Dec 2016 | % Actual Expenditures Dec 2016 | Total Expected Dec 2016 | % Expected Dec 2016 | Cumulative Expenditure Dec 2016 | % Actual Expenditures Dec 2016 | Total Expected Dec 2016 | % Expected Dec 2016
23.01,03 | Consultancy | 55000 | 35000 | 0 | 0 | 90000
23.02,07 | Training | 60000 | 90000 | 100000 | 90000 | 340000
23.04,06 | Goods | 0 | 280000 | 130000 | 0 | 410000
23.05 | Non-consult. Service | 0 | 120000 | 120000 | 120000 | 360000
TOTAL |  | 115000 | 525000 | 350000 | 210000 | 1200000 | 166785 | 13.8987 | 640000 | 53.3333 | 0 | 0 | 990000 | 82.5 | 0 | 0 | 0 | 0
Component 4: Project Management
Budget lines | Category | Y 1 | Y 2 | Y 3 | Y 4 | TOTAL | Cumul Expend Dec 2015 | % Expenditure | Total Expected Dec 2015 | % Expected Dec 2015 | Cumulative Expenditure Dec 2016 | % Actual Expenditures Dec 2016 | Total Expected Dec 2016 | % Expected Dec 2016 | Cumulative Expenditure Dec 2016 | % Actual Expenditures Dec 2016 | Total Expected Dec 2016 | % Expected Dec 2016
23.01,03 | Consultancy | 46250 | 50750 | 38250 | 50750 | 186000
21.03/21.04/21.07/21.08 | Training | 8000 | 0 | 0 | 0 | 8000
21.05 | Travel costs | 14000 | 14000 | 14000 | 14000 | 56000
TOTAL |  | 68250 | 64750 | 52250 | 64750 | 250000 | 64816 | 25.9264 | 133000 | 53.2 | 0 | 0 | 185250 | 74.1 | 0 | 0 | 0 | 0
[5 empty] | TOTAL | 3000000 | 535678 | 17.8559
| EXPECTED AND ACTUAL EXPENDITURES |  |  | (Percentage, Dec 2015)
|  | Compon. 1 | Compon. 2 | Compon. 3 | Compon. 4 | TOTAL
| Expected | 55.3 | 49.4 | 53.2 | 53.2 | 53.2
| Actual | 19.5255 | 19.7045 | 13.8987 | 25.9264 | 17.8559

## Web
LIST OF INITIAL DOCUMENTATION POSTED ON THE WEB SITE
| Creation of Web site (Yes=1; No=0) | 0
| Number of documents posted: | 0
| Number of Web site visitors | 0

## GEF TT
²
GEF International Waters Tracking Tool
|  | NOTE: Please address all boxes colored blue |  |  | GEF Project ID: 3809 | GEF Implementing Agency: World Bank
Project Title: Red Sea and Gulf of Aden Strategic Ecosystem Management Regional Project
|  | Select GEF Replenishment: | GEF-5 |  | GEF Allocation ($USD): 3.0 million | Countries: Djibouti, Egypt, Jordan, Sudan, Yemen
| A | PROCESS INDICATORS
Select project's Operational Program(s), Strategic Program(s), or objective(s) below. If multiple OP/SP/Obj is appropriate for a given indicator then select "Multiple" from the dropdown list:
|  |  | OP/SP/Obj 1 | OP/SP/Obj 2
|  | Indicators | Scroll down menu of ratings |  | Notes: | Ratings
| 1 | Regional legal agreements and cooperation frameworks | 4 |  | Jeddah convention signed and ratified by PERSGA member countries and Regional institution established | 1 = No legal agreement/cooperation framework in place 2 = Regional legal agreement negotiated but not yet signed 3 = Countries signed legal agreement 4 = Legal agreement ratified and entered into force
| 2 | Regional management institutions (RMI) | 4 |  | Country contributions to PERSGA are well above 50% | 1 = No RMI in place 2 = RMI established but functioning with limited effectiveness, < 50% countries contributing dues 3 = RMI established and functioning, >50% of countries contributing dues 4 = RMI in place, fully functioning and fully sustained by at or near 100% country contributions
| 3 | Management measures in ABNJ incorporated in Global/Regional Management Organizations (RMI) institutional/ management frameworks | 4 |  | The Red Sea and Gulf of Aden are narrow water bodies, where all waters are either within territorial waters or within the exclusive economic zone . This makes most waters under national management. Due to this geographic feature exclusive economic zones between countries are midwater lines. PERSGA serves as the Regional Organization for coordination of management of these waters between member countries | 1 = No management measures in ABNJ in (RMI) institutional/ management frameworks 2 = Management measures in ABNJ designed but not formally adopted by project participants 3 = Management measures in ABNJ formally adopted by project participants but not incorporated in RMI institutional/management frameworks 4 = Management measures in ABNJ fully incorporated in RMI institutional/ management frameworks
| 4 | National Inter-Ministry Committees (IMCs) | 4 |  | Hamata / Wadi el Jimal Protected Area is managed by an Inter-Ministry Committee and a Local Committee including the Local Community and Stakeholders. Aqaba Special Economic Zone Authority in Jordan is a local government that has the mandate of all ministries in the Aqaba Region Dungonab and Mohammad Gol Protected Area is managed by Sudanese Wile Life through an Inter-Ministry arrangement between Federal Ministry of Interior, Federal Ministry of Environment and Red Sea State Ministry of Environment | 1 = No IMCs established 2 = IMCs established and functioning, < 50% countries participating 3 = IMCs established and functioning, > 50% countries participating 4 = IMCs established, functioning and formalized thru legal and/or institutional arrangements, in most participating countries
| 5 | National/Local reforms | 4 |  | National legal reforms adopted with technical enforcement in managing marine areas in three countries at least Jordan and Egypt and Sudan | 1 = No national/local reforms drafted 2 = National/ local reforms drafted but not yet adopted 3 = National/legal reform adopted with technical/enforcement mechanism in place 4 = National/ legal reforms implemented
| 6 | Transboundary Diagnostic Analysis (TDA): Agreement on transboundary priorities and root causes | 4 |  | Regional Agreement in Place and its regional tools operational. Regional Organization for Conservation of the Environment of the Red Sea and Gulf of Aden "PERSGA" is fully operational with Headquarters hosted in Saudi Arabia. Center of Emergency Mutual Aid in the Red Sea and Gulf of Aden " EMARSGA" is fully operational with Headquarters hosted in Egypt. Several protocols established covering collaboration in protection of the marine environment in the Red Sea and Gulf of Aden | 1 = No progress on TDA 2 = Priority TB issues identified and agreed on but based on limited effect information; inadequate root cause analysis 3 = Priority TB issues agreed on based on solid baseline effect info; root cause analysis is inadequate 4 = Regional agreement on priority TB issues drawn from valid effect baseline, immediate and root causes properly determined
| 7 | Revised Transboundary Diagnostic Analysis (TDA)/Strategic Action Program (SAP) including Climatic Variability and Change considerations | 4 |  | Following the development of main SAP, sub SAPs for specific concerns such as protection of the marine environment from land based sources of pollution are prepared in most countries PERSGA has adopted a strategy for Climate Change Adaptation and assessment studies have been conducted in most Member States. PERSGA also participates regularly in Climate Change COPs and organizes side events with its member states | 1 = No revised TDA or SAP 2 = TDA updated to incorporate climate variability and change 3 = revised SAP prepared including Climatic Variability and Change 4= SAP including Climatic Variability and Change adopted by all involved countries
| 8 | TDA based on multi-national, interdisciplinary technical and scientific (MNITS) activities | 3 |  | PERSGA has supported Monitoring activities in all its member states. This resulted in National Monitoring Programs of the Coastal and Marine Environment. Some of these monitoring program are regular and sustained by the countries and some are not. Data generated in these monitoring programs feed in a Regional database at PERSGA. Results are not yet posted on the Web site, but technical administrative measures to do that are under discussion | 1 = TDA does not include technical annex based on MNITS actives 2 = MNITS committee established and contributed to the TDA development 3 = TDA includes technical annex, documenting data and analysis being collected 4 = TDA includes technical annex posted IWLEARN and based on MNITS committee inputs
| 9 | Development of Strategic Action Plan (SAP) | 3 |  |  | 1 = No development of SAP 2 = SAP developed addressing key TB concerns spatially 3 = SAP developed and adopted by ministers 4 = Adoption of SAP into National Action Plans (NAPs)
| 10 | Proportion of Countries that have adopted SAP | 7/7 |  |  | Number of countries adopted SAP / total number of countries - e.g.. 3 countries adopted /10 total countries in project, so 3/10
| 11 | Proportion of countries that are implementing specific measures from the SAP (i.e. adopted national policies, laws, budgeted plans) | 7/7 |  |  | Number of countries implementing adopted SAP / total number of countries - e.g.. 3 countries implementing /10 total countries in project, so 3/10
| 12 | Incorporation of (SAP, etc.) priorities with clear commitments and time frames into CAS, PRSPs, UN Frameworks, UNDAF, key agency strategic documents including financial commitments and time frames, etc | 4 |  | Most countries have considered the SAP in their development / assistance framework. In Fact some countries request having PERSGA as a partner in their National Assistance programs with UN organizations. Examples are UNDP interventions in Djibouti and Sudan. PERSGA also directly manages a number off assistance programs with some UN organizations for the benefit of the countries. Examples on this are the Program of Protection of the Marine Environment from Landbased Pollution Sources in collaboration with UNEP; and the Technical Cooperation Program of the International Maritime Organization IMO for Protection of the Marine Environment from Pollution from Marine sources "ship based activities". | 1 = No progress 2 = Limited progress, very generic with no specific agency/government(s) commitments 3 = Priorities specifically incorporated into some national development/assistance frameworks with clear agency/government(s) commitments and time frames for achievement 4 = Majority of national development/assistance frameworks have incorporated priorities with clear agency/government(s) commitments and time frames for achievement
| B | STRESS REDUCTION INDICATORS
|  | Indicators | Scroll down menu of ratings |  |  | Ratings
| 13 | Are there mechanisms in place to produce a monitoring report on stress reduction measures? | 4 |  | Database exists and receives regular updates from National Monitoring Programs. Recently an online Monitoring Initiative has been started where data is timely received at PERSGA Headquarters. The initiative started in Aqaba Jordan and securing fund is in progress to have the initiative spread to cover all member states | 1 = No mechanisms in place to monitor/report change 2 = Some national/regional monitoring mechanisms, but they do not satisfy the project related indicators. 3 = monitoring mechanisms in place for some of the project related indicators 4 = Mechanisms in place and sustainable for long-term monitoring
| 14 | Stress reduction measurements incorporated by project under management of: | Choose Management Mechanism from list below: | Please specify the area currently under protection out of total area identified by project below (e.g. 10,000/100,000 Ha): |  | Management Mechanisms: 1 = Integrated Water/River Resource Management (Watershed, lakes, aquifers) 2 = Integrated Coastal Management (Coast) 3 = Marine Spatial Planning (Marine) 4 = Marine Protected areas (Fisheries/ABNJ)
4
| 15 | Please specify the types of technologies and measures implemented in local investments (Column D) and their respective results (Column I):
|  | Local investment #1 | Stress Reduction Measurements (Choose up to five) |  |  | Please enter amount/value of respective stress reduction below:
|  |  | 1 | 1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
4
6
10
15
|  | Local investment #2 | Stress Reduction Measurements (Choose up to five) |  |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
|  | Local investment #3 | Stress Reduction Measurements (Choose up to five) |  |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
NOTE: If the project has more than three local investments, please fill out the Annex A found in the worksheet tabs below.
| C | WATER, ENVIRONMENTAL & SOCIOECONOMIC STATUS Indicators
|  | Indicators | Scroll down menu of ratings |  |  | Ratings
| 16 | Are there mechanisms and project indicators in place to monitor the environmental and socioeconomic status of the waterbody? | 4 |  |  | 1 = No mechanisms in place 2 = Some national/regional monitoring mechanisms, but they do not satisfy the project related indicators. 3 = Monitoring mechanisms in place for some of the project related indicators 4 = Mechanisms in place for project related indicators and sustainable for long-term monitoring
| D | IW:LEARN Indicators
|  | Indicators | Scroll down menu of ratings |  |  | Ratings
| 17 | Participation in IW events (GEF IWC, Community of Practice (COP), IW:LEARN) | 3 |  | PERSGA participates regularly in IW events. The SEM Project specifically has participated in a workshop on construction of websites according to IW learn guidelines and in the 17th Annual Consultative Committee Meeting on Large Marine Ecosystems (LME) in 29th September to 2nd October 2015. | 1 = No participation 2 = Documentation of minimum 1 event or limited COP participation 3 = Strong participation in COPs and in IWC 4 = Presentations with booth participation and hosting of staff/twinning
| 18 | Project website (according to IW:LEARN guidelines) | 4 |  | PERSGA Web site is up and running covering in brief all SEM Project activities. A dedicated web site of the SEM Project is under construction | 1 = No project website 2 = Website not in line with IW:LEARN guidelines, not regularly updated 3 = Website in line with IW:LEARN guidelines, not regularly updated 4 = Website in line with IW:LEARN guidelines, regularly updated
[5 empty] | Date Completed: | 01 29 2016

## GEF Annex
GEF IW Tracking Tool - Annex A: Additional Local Investments
15 | Please specify the types of technologies and measures implemented in local investments (Column D) and their respective results (Column I):
| Local investment #4 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
| Local investment #5 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
| Local investment #6 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
| Local investment #7 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
| Local investment #8 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
| Local investment #9 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
| Local investment #10 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
| Local investment #11 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less:
| Local investment #12 | Stress Reduction Measurements (Choose up to five) |  | Please enter amount/value of respective stress reduction below:
1 = Municipal wastewater pollution reduction - N, P & BOD (kg/yr) 2 = Industrial wastewater pollution reduction - pollutant; estimated kg/yr 3 = Agriculture pollution reduction practices - ha of practices; estimate of N, P & BOD kg/yr 4 = Restored habitat, including wetlands - ha restored 5 = Conserved/protected wetland, MPAs, and fish refugia habitat - ha applied 6 = Reduced fishing pressure - tons/yr reduction; % reduction in fleet size 7 = Improved use of fish gear/techniques - % vessels applying improved gear/techniques 8 = Water use efficiency measures - m^3/yr water saved 9 = Improved irrigation practices - m^3/ha/yr water saved 10 = Alternative livelihoods introduced - # people provided alternative livelihoods 11 = Catchment protection measures - ha under improved catchment management 12 = Aquifer pumping reduction - m^3/yr water saved 13 = Aquifer recharge area protection - ha protected 14 = Pollution reduction to aquifers - kg/ha/year reduction 15 = Invasive species reduction - ha and/or #'s of targeted area 16 = Other - please specify in box below
Briefly describe investment in a 100 words or less: